## Sheet1
Six Months Deliverables from July to December 2015
Months | No. of Weeks | Task | Description
July | 1st | looking into problems of valves/shower controlling | studying working mechanism and listing points to be taken in notice
| 2nd | circuit designing of controlling system | working on design over minimization and suitable for kit
| 3rd - 4th | implementation of controlling system | mounting the components and checking its continuity
August | 1st | finalizing circuit | finalizing its testing and making it presentable
| 2nd | looking for problems related to solar panel | studying working mechanism and listing points to be taken in notice
| 3rd - 4th | code integration and implementation | working on design over minimization, suitable for kit and writng of code wherever needed
September | 1st | finalizing module | finalizing its testing and making it presentable
| 2nd - 3rd | looking for problems of agriculture kit size minimization | listing points to be taken in notice
| 4th | circuit design of kit | working on design over minimization and suitable for kit
October | 1st
| 2nd - 3rd | implementation of kit | mounting the components and checking its continuity
| 4th | testing of kit | looking for flaws
November | 1st- 2nd | kit makeover with casing | making complete kit presentable
3rd - 4th
December | 1st - 2nd | integration of all the modules into single kit | working of all the kits from minimization to making them into one
3rd
4th