## Sheet1
Six Months Deliverables from July to December 2015(Software Development)
Months | Weeks of Year 2015 | Task | Description
July-August | 27-29 | Analize working of Arduino software and its layers. | Study working mechanism of underlying embedded compiler(gcc and avrdude) and prepare an SRS report for future application.
| 30-32 | Start developing User friendly GUI | Develop a user interface design for hardware support with customized features
August | 33-35 | Test and debug the application | Exhibit finalized version of application.
September | 36-38 | Evaluate the existing web application and append user friendly database conectivity. | User friendly step by step database conection establishment and database formation through web interface.
September-October | 39-41 | Review complete software flow. | Critically analize software features and implement flawless software package from user perspective.
| 42-44 | Study open source cloud platforms and integration process. | Propose step wise procedure for cloud integration and prepare a writeup on future plan.
November | 45-47 | Explore cloud integration development. save sensor data on cloud. | Detailed analysis of data storage on cloud and study usage of cloud services. Complete cloud integration with database storage capabilities.
November-December | 48-50 | Explore dashboard services and development | Start developing dashboard application
| 51-53 | Test and debug complete software chain. | Complete achievement of six months deliverables done.